## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 2 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
INDEX | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week 1 (Aug 20 - Aug 26) | [6 empty] | Week 2 (Aug 27 - Sept 2) | [6 empty] | Week 3 (Sept 3 - Sept 9) | [6 empty] | Week 4 (Sept 10 - Sept 16) | [6 empty] | Week 5 (Sept 17 - Sept 23) | [6 empty] | Week 6 (Sept 24 - Sept 30) | [6 empty] | Week 7 (Oct 1 - Oct 7) | [6 empty] | Week 8 (Oct 8 - Oct 14) | [6 empty] | Week 9 (Oct 15 - Oct 21) | [6 empty] | Week 10 (Oct 22 - Oct 28) | [6 empty] | Week 11 (Oct 29 - Nov 4)
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77
NestScout Real Estate Listing Website
Phase 1 Requirements Elicitation |  | 1 | 14 | 1 | 13 | 100%
1 | Determine Project Purpose and Desired Outcome | 1 | 2 | 1 | 1 | 100%
2 | Determine Target Users and User Scenarios | 3 | 1 | 3 | 1 | 100%
3 | Define Assumptions and Constraints | 4 | 1 | 4 | 1 | 100%
4 | Define Functional and Non-Functional Requirements | 5 | 2 | 5 | 2 | 100%
5 | UI Mockups | 7 | 3 | 6 | 2 | 100%
6 | Define Data Dictionary | 10 | 2 | 10 | 1 | 100%
7 | Initial Use Case Model | 12 | 3 | 12 | 2 | 100%
Phase 2 Requirements Analysis |  | 15 | 14 | 17 | 9 | 100%
8 | Refine Use Case Model | 15 | 2 | 16 | 2 | 100%
9 | Build Class Diagram | 22 | 6 | 22 | 4 | 100%
10 | Sequence Diagram | 22 | 7 | 22 | 4 | 100%
Phase 3 Design and Implementation |  | 29 | 26 | 30 | 26 | 100%
Design |  | 29 | 7 | 30 | 6 | 100%
11 | Design Model and System Architecture | 29 | 3 | 30 | 2 | 100%
12 | Design and Implement User Interface using CSS | 29 | 3 | 31 | 2 | 100%
Database System
13 | Develop Database Schema | 33 | 2 | 33 | 2 | 100%
14 | Database Creation and Configuration | 34 | 3 | 34 | 3 | 100%
Property Listing
15 | Create and Delete Property | 36 | 4 | 36 | 4 | 100%
16 | Searching System | 37 | 3 | 37 | 2 | 100%
17 | Browse By Category | 39 | 3 | 38 | 3 | 100%
18 | Display Property on Map | 42 | 3 | 43 | 2 | 100%
Account Manager
19 | Registration and Login Activities | 46 | 4 | 46 | 5 | 100%
20 | Edit Account Details | 48 | 2 | 48 | 2 | 100%
21 | Messenger System | 49 | 6 | 49 | 7 | 100%
22 | Appointment System | 49 | 4 | 49 | 4 | 100%
Phase 4 Testing and Demo |  | 55 | 20 | 54 | 21 | 100%
23 | Code Finalization | 55 | 6 | 55 | 6 | 100%
24 | Testing and Debugging | 61 | 5 | 61 | 5 | 100%
25 | Final Documents | 63 | 11 | 63 | 10 | 100%
26 | Preparing for Demo | 64 | 11 | 63 | 12 | 100%